## ProjectSchedule
2025/2026 TET Development | [6 empty] | ► Watch How to Make a Gantt Chart in Excel
Project: Durham Heart |  | Project Start: | 2025-10-15
Led by: Katrina Lai |  | Today: | 2025-12-10
|  | Display Week: | 1 |  |  | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01
 | time axis 2025-10-13 to 2025-12-07
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2025-10-13 to 2025-12-07
Improvement Integration
Calculate the power loss of the current ltspice circuit on LTSpice, and implement improvements (eg. Replace componets, redesign) | Joe Gater, Samuel Finney | 80% | 2025-10-15 | 2025-10-29 | 15
Develop and simulate gate-drive PWM control for the inverter using the ESP32 module in Wokwi (see connection on KiCAD Schematics) | Lavirotte Renan, Alex Johnson | 100% | 2025-10-15 | 2025-10-22
KiCAD PCB routing learning | Alex Johnson, Femi, Scarlett | 80% | 2025-10-23 | 2025-10-29
Construct rectifier and boost converter KiCAD schematics | Joe Gater, Samuel Finney, Alex | 0% | 2025-10-30 | 2025-11-05
Develop and simulate gate-drive PWM control for the rectifier in Wokwi. | Lavirotte Renan, Alex Johson | 90% | 2025-10-30 | 2025-11-05
Frequency Tuning mechanism elucidation, method determination, and system development using LTSpice | Joe Gater, Samuel Finney, Ahaan | 40% | 2025-10-15 | 2025-11-05 | 22
Simulate vertical, lateral, and radial coil misalignment effect on coupling, field, and losses using COMSOL, and determine the alignment tolerance | Aoife McGuire, Anas | 10% | 2025-10-15 | 2025-11-05 | 22
Coil testing design and conduction (max temperature to be measured); root cause analysis, and solution development; chracteristics extraction | Lim Zheng, Katrina Lai | 0% | 2025-10-15 | 2025-11-05 | 22
Motor control invetigation, component selection and circuit construction for motor control in KiCAD Schematics | Meg Croft, Kian Nooralahiyan, Alex | 35% | 2025-10-15 | 2025-11-05
Research into the importance, and integration of sesnors into the current block diagram: pressure senor, flow sensor, motor sensor, ECG sensor, etc | Sam Scandler, Clara Jang, Edmond | 0% | 2025-10-15 | 2025-11-05
Motor geometry optimisation using ANSYS | Scarlett, Roufus, Cody | 70% | 2025-10-15 | 2025-11-05
External and internal battery hunting, and charge control component selection, and circuit design in KiCAD Schematics; calculate required external battery volatge through reverse engineering | Ahaan , Habib Mosa, Femi | 0% | 2025-10-15 | 2025-11-05
Phase 2 Design Assembly
Assemble all internal KiCAD schematics | Joe Gater, Kian Nooralahiyan | 0% | 2025-11-06 | 2025-11-12 | 7
Internal PCB construction | Joe Gater, Lavirotte, Anas, Kian Nooralahiyan | 0% | 2025-11-06 | 2025-11-26
Powerpoint Preparation for Conference | All | 0% | 2025-11-05 | 2025-11-19 | 15
Build KiCAD schemtics for frequency tuning | Samuel Finney, Joe Gater | 0% | 2025-11-06 | 2025-11-12 | 7
Assemble all external KiCAD schematics | Samuel Finney, Joe Gater | 0% | 2025-11-13 | 2025-11-19 | 7
External PCB construction | Samuel Finney, Alex Johnson, Joe Gater | 0% | 2025-11-13 | 2025-11-26
Develop code for motor drive PWM control | Lavirotte Renan, Kian Nooralahiyan | 0% | 2025-11-06 | 2025-11-19
Design wireless communication system across skin for sensor data transmission, and data storage | Sam Scandler, Clara Jang | 0% | 2025-11-06 | 2025-11-19
Coil reconstruction/ANSYS simulation close to reality | Lim Zheng, Anas | 0% | 2025-11-06 | 2025-11-19
COMSOL result summarisation and graph generation, simulate circuit behaviour in LTSpice under misalignment | Ahaan Jaisinghani, Aoife McGuire | 0% | 2025-11-06 | 2025-11-26
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com |  |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.